## Weekly Progress
WCTE Project Weekly Progress Tracker
Arkaprava Ghosh - DA25C003
Reporting to: Ramesh sir (CTO) and Kavitha mam (Tech Lead)
Reporting period: 24 August–25 October 2026 ¦ Updated: 21 October 2026
Week and date range | Work completed / in progress | Bottlenecks faced
Week 1 24–30 August 2026 | • Met Ramesh sir and Kavitha mam on 27 August. • Discussed practical ML problems, factory automation challenges, and possible project directions. | • Needed to finalise a suitable, high-impact problem statement.
Week 2 31 August–6 September 2026 | • Reviewed the existing VisureX approach and project poster. • Researched operator logbook digitization for MSMEs. • Drafted and submitted initial proposal on 2 September: Hands-free logbook & production tracking using Meta Glasses, ArUco marker gaze locks, mobile edge proxy, and CV dial/tray reading. | • Changes in ambient factory lighting and camera orientation affected reading stability. • Wearable hardware constraints and edge processing reliability raised feasibility questions.
Week 3 7–13 September 2026 | • Explored Meta glasses workflow feasibility vs. fixed industrial inspection. • Researched optical capture bounds, Bluetooth bandwidth limits, and display parsing models. • Coordinated technical review on MSME shop-floor ergonomics and deployment costs. | • Capture latency and battery constraints in harsh industrial settings. • Need to evaluate whether wearable glasses or fixed-surface visual inspection provides higher industry demand.
Week 4 14–20 September 2026 | • Pivoted project scope toward automated flat surface quality inspection. • Submitted revised project abstract on 15 September: Integrated visual inspection platform combining 2D surface anomaly detection with Automated Optical Inspection (AOI) for solar panels and sheet materials. • Defined the dual-engine concept: classical CV for preprocessing and ML for defect segmentation. | • Narrowing down specific anomaly classes and defining quantifiable severity criteria. • Limited public availability of pixel-level defect masks.
Week 5 21–27 September 2026 | • Conducted literature review on solar photovoltaic (PV) soiling and defect inspection. • Formulated project boundary: in-scope stains (dust/soiling, bird droppings, mud) vs. out-of-scope defects (snow, mechanical cracks, electrical burns). • Prepared initial architectural proposal comparing single-stage classifiers against two-stage segmentation. | • Scheduled review meeting was postponed due to team travel. • Most public datasets only provide image-level labels rather than pixel-level segmentation masks.
Week 6 28 September–4 October 2026 | • Attended technical review on 28 September with Ramesh sir and Kavitha mam. • Finalized the two-stage inspection architecture: Stage A for panel localization/rectification and Stage B for stain segmentation. • Defined explainability goals: replacing black-box classification with exact stain coverage % and localized hotspot alerts. | • Background artifacts (sky, roof tiles, shadows) distort coverage metrics if panels are not strictly rectified. • Need for a robust boundary-detection baseline.
Week 7 5–11 October 2026 | • Attended meeting at WCTE Centre on 7 October discussing plausible datasets for model training. • Evaluated public repositories: Kaggle (Faulty Solar Panel Images), Mendeley Data (Solar Panel Soiling), and Roboflow Universe. • Designed data-hygiene protocol: Perceptual Hashing (pHash) to detect duplicate web images and prevent train–test leakage. | • Reused images across public repositories cause severe train–test data leakage. • Extreme class imbalance between large clean areas and small, high-risk bird droppings.
Week 8 12–18 October 2026 | • Set up local development environment (Python 3.12, PyTorch, Albumentations, SMP, OpenCV). • Finalized operational decision rules: High Stain if Coverage ≥ 10% or any single bird blob ≥ 2%; 4×4 sub-panel grid breakdown. • Implemented Stage A perspective homography rectifier to canonical 512×512 view. • Formulated dataset curation pipeline: pHash deduplication, 70/15/15 group-stratified splits, and SAM 2/CVAT-aligned ground-truth mask preparation. | • Ensuring augmentations avoid hue shifts that misrepresent dust tones. • Adapting models and training pipelines for efficient CPU execution.
Week 9 — ongoing 19–25 October 2026 | • Ingested and standardized multi-source datasets (Kaggle, Mendeley, Roboflow) into unified manifest. • Model is currently in the training process for the computer vision solar panel stain detection and segmentation network. • Monitoring training iterations, batch scheduling, and convergence across initial epochs. | • Training execution time on local workstation hardware. • Balancing batch size and memory footprint during segmentation training.